## RTM
Requirements Traceability Matrix (Sample Template)
Author: | Nathaniel Enrique Catalan Eulin
PROJECT TITLE: | SHUFFLE
PROJECT DESCRIPTION: | A playing card memorization software that let's you train your card memorization skills, track your progress, detect your inconsistencies to lead you to your Memory Olympic dreams (or just improve your memory).
TARGET USER/S: | Gabriel Badeo
SDLC Used: | AGILE: the project will be implemented in Agile to be enable flexibility (especially in adjusting requirements)and bring out results as fast as possible.
Technology Stack: | ELECTRON: A tool for creating cross-platform apps that uses web developlment tech-stack (HTML, CSS, JS). I will use this because I am familiar only with using these tech stacks, and this tool will help me create a desktop application. Also, because it is widely use.
| a) Front-end: |  | HTML, CSS, JS (in Electron)
| b) Back-end: |  | NODE.JS (in Electron)
Note: Put all your files in your main Google Drive folder. Use your Full Name as the folder name during submission of the requirements below. The requirements below should be grouped in subfolders containing the same type of requirement/diagram.
PART I. SOFTWARE PROJECT REQUIREMENTS
(A) REQUIREMENTS ELICITATION | [5 empty] | (B) REQUIREMENTS SPECIFICATION | [15 empty] | (C) DESIGN MODELS (put at least one type of diagram per workflow dimension here. You can construct many diagrams of the same type depending on the size of your project requirements.) | [8 empty] | (D) IMPLEMENTATION | [7 empty] | (F) DEMO (Provide a link to recorded demo videos simulating the user stories/cases in the package)
[22 empty] | (C.1) CASE DIMENSION |  |  | (C.2) PROCESS DIMENSION |  |  | (C.3) RESOURCE DIMENSION
USER STORY | [5 empty] | (B.1) USE CASE |  |  |  | (B.2) Feature/Functionality |  |  |  | (B.3) GUI Storyboard (put all storyboards in one folder) |  |  | (B.4) TEST SPECIFICATION (update the status whenever applicable) |  |  |  |  | (C.1.1) Use Case Diagram (example) |  |  | (C.2.1) Sequence Diagram (example) |  |  | (C.3.1) Class Diagram (example) |  |  | (D.1) Package Diagram (Resource Dimension) |  |  | (D.2) Feature/Functionality (same as (B.2)) |  |  | (D.3) Schema (Provide a link to the screenshot/file of the Schema used per package
Story ID | Description | Cost Estimate | User | Date Recorded | Version No. | ID | Link to Use Case | Cost Estimate | Priority | ID | Name | Description | Module/Package | ID | Link to Diagram | Status (Ongoing/Completed/Cancelled/NA) | ID | Link to Test Case | Type of Test (Unit/Module/System/User Acceptance) | Status (Pass/Failed/NA) | Feedback/ Remarks | ID | Link to Diagram | Status (Ongoing/Completed/Cancelled/NA) | ID | Link to Diagram | Status (Ongoing/Completed/Cancelled/NA) | ID | Link to Diagram | Status (Ongoing/Completed/Cancelled/NA) | ID | Link to Diagram | Status (Ongoing/Completed/Cancelled/NA) | ID | Name | Status (Ongoing/Complete/Tested/Accepted/Cancelled) | ID | Link to Screenshot/File | ID | Link to Video Demo
# | <Description> | <cost estimate to develop story> | <put the name of the user who gave this requirement> | <Put the date this story is recorded as part of your project requirement> | <put the version number of the story, if the story was changed by the user> | cs101 | https://drive.google.com/file/d/1N5WQV7fvaMaISNWYUyK3ftFNr3MIAZJX/view?usp=drive_link | 2 | High | ft_u101 | add_user | adds user in the app[ | shuffle_user | sb_configure_session | https://drive.google.com/file/d/1N7rtsPYbiRp70mILki-7TYVoDoK_LXho/view?usp=drive_link | Ongoing | [5 empty] | use_case_diagram_1 | https://drive.google.com/file/d/1NNLg3C6aVwJAuhFyAFO813s2T1uylm15/view?usp=drive_link | done | # | https://drive.google.com/file/d/1NNLg3C6aVwJAuhFyAFO813s2T1uylm15/view?usp=drive_link | done | class_diagram_01 | https://drive.google.com/file/d/1NNLg3C6aVwJAuhFyAFO813s2T1uylm15/view | on going | package_diagram_01 | https://drive.google.com/file/d/1NaR_wIGsYPhU_Ti5f2MTYXqsPf56iA5u/view?usp=sharing | done | config_ui | Session Configuration UI | Ongoing | schema_diagram | https://drive.google.com/file/d/1Naf8Y_qc3b6ctH0Dya1JPGdve4oPePc8/view?usp=drive_link | #
cs100 | a user, I want to be able to start setting up the configurations of my training session | 2 hours | Gabriel Badeo | 03.08.2024 | 1 | cs201 | https://drive.google.com/file/d/1N5W2M3qxRkKnQFCDc2VCnxxn2q0sMyKZ/view?usp=drive_link | 2 | High | ft_u102 | delete_user | delete's user in the app | shuffle_user | sb_login_signup | https://drive.google.com/file/d/1N7qvZ7KNguPOWFfiNxZwNkPKp_NJ9-nO/view?usp=drive_link | Ongoing | [9 empty] | https://drive.google.com/file/d/1NNLg3C6aVwJAuhFyAFO813s2T1uylm15/view?usp=drive_link | done | [6 empty] | mem_nav | Memorization Session Navigation | Ongoing
cs200 | As a user, I want to be able to determine the number of decks that I am trying to memorize in my training session | 2 hours | Gabriel Badeo | 03.08.2024 | 1 | cs301 | https://drive.google.com/file/d/1N5OACxph0uJsHu0E045zcweuIurYHRZ0/view?usp=drive_link | 2 | High | ft_u201 | log_in_user | lets a user log in | shuffle_user | sb_memorization_session | https://drive.google.com/file/d/1N7moOMRJvPAJAt0O2Vk8ej_lbSSQ_ReO/view?usp=drive_link | Ongoing | [9 empty] | https://drive.google.com/file/d/1NNLg3C6aVwJAuhFyAFO813s2T1uylm15/view?usp=drive_link | done | [6 empty] | mem_ui | Memorization Session UI | Ongoing
cs300 | As a user, I want to be able to determine the number of cards per deck of my training session | 2 hours | Gabriel Badeo | 03.08.2024 | 1 | cs401 | https://drive.google.com/file/d/1N5MZU0an0_zq4NZk5cnF7MgyoxAD-tJQ/view?usp=drive_link | 2 | High | ft_u202 | log_out_user | lets a user log out the app | shuffle_user | sb_ordering_session | https://drive.google.com/file/d/1N7UBKNwy6W-daXRpmVnU2xB3Vz-HVfDz/view?usp=drive_link | Ongoing | [9 empty] | https://drive.google.com/file/d/1NNLg3C6aVwJAuhFyAFO813s2T1uylm15/view?usp=drive_link | done | [6 empty] | fill_list_ui | Fill list recall session ui | Ongoing
cs400 | As a user, I want to be able to choose whether to make my session `timed` or `zen` mode | 2 hours | Gabriel Badeo | 03.08.2024 | 1 | cs501 | https://drive.google.com/file/d/1N5MZU0an0_zq4NZk5cnF7MgyoxAD-tJQ/view?usp=drive_link | 2 | High | ft_cs101 | configure_session | shows all the configurations the user can set | configure_session | sb_progress | https://drive.google.com/file/d/1N7IosZlSnNmCn9_TBG-VyEuKimWaiIg4/view?usp=drive_link | Ongoing | [9 empty] | https://drive.google.com/file/d/1NNLg3C6aVwJAuhFyAFO813s2T1uylm15/view?usp=drive_link | done | [6 empty] | fill_list_logic | Fill list recall session logic | Ongoing
cs500 | As a user, I want to be able to decide what the shuffling method will be: a normal one (how a human would normally shuffle) or standard (*Pseudo-Random Number Generator* algorithm in competitions) | 2 hours | Gabriel Badeo | 03.08.2024 | 1 | cs601 | https://drive.google.com/file/d/1N549y2DcgI_bXAGli6FyoSHeu2BhkapA/view?usp=drive_link | 2 | High | ft_cs201 | configure_no_deck | lets user configure the number of decks in session | configure_session | [12 empty] | https://drive.google.com/file/d/1NNLg3C6aVwJAuhFyAFO813s2T1uylm15/view?usp=drive_link | done | [6 empty] | comp_ui | Simultaneaous comparison recall session ui | Ongoing
cs600 | As a user, I want to be able to choose what ordering method should I use: *simultaneous comparison/recitation* or *Sequence listing* | 2 hours | Gabriel Badeo | 03.08.2024 | 1 | ts101 | https://drive.google.com/file/d/1N2vlDwdtTJxQ4IQqm64mEaTmSzM_q7cW/view?usp=drive_link | 2 | High | ft_cs301 | configure_no_cards | lets user configure the number of cards per deck in session | configure_session | [12 empty] | https://drive.google.com/file/d/1NNLg3C6aVwJAuhFyAFO813s2T1uylm15/view?usp=drive_link | done | [6 empty] | comp_logic | Simultaneaous comparison recall session | Ongoing
ts100 | As a user, I want to be able to navigate back and forth through a deck | 2 hours | Gabriel Badeo | 03.08.2024 | 1 | ts102 | https://drive.google.com/file/d/1N2m0M5bwLNzWB7VfTaR4VB-JB04OZ2eK/view?usp=drive_link | 2 | High | ft_cs401 | configure_time | lets user choose either time or zen mode | configure_session | [12 empty] | https://drive.google.com/file/d/1NNLg3C6aVwJAuhFyAFO813s2T1uylm15/view?usp=drive_link | done | [6 empty] | std_shuffle_logic | Standard Shuffling Logic | Ongoing
ts101 | As a user, I want to be able to peak through the topmost cards (to up to 7 cards) | 2 hours | Gabriel Badeo | 03.08.2024 | 1 | ts103 | https://drive.google.com/file/d/1N6YlR0FCMiN7AqwyhObQIJSUmMnA8Rco/view?usp=sharing | 2 | High | ft_cs501 | configure_shuffle | lets user choose what shuffling method to use | configure_session | [12 empty] | https://drive.google.com/file/d/1NNLg3C6aVwJAuhFyAFO813s2T1uylm15/view?usp=drive_link | done | [6 empty] | nl_shuffle_logic | Normal Shuffling Logic | Ongoing
ts102 | As a user, I want to be able to reduce the number of peaked cards | 2 hours | Gabriel Badeo | 03.08.2024 | 1 | ts104 | https://drive.google.com/file/d/1N2jteN-mwwFoZdnWJIYET25pV1s6fD-t/view?usp=drive_link | 2 | High | ft_cs601 | configure_order_method | lets user choose what ordering method to use (comparison or sequence listing) | configure_session | [12 empty] | https://drive.google.com/file/d/1NNLg3C6aVwJAuhFyAFO813s2T1uylm15/view?usp=drive_link | done | [6 empty] | deck_ds | Deck of cards data structure | Ongoing
ts103 | As a user, I want to be able to shift (bring to bottom) the topmost card | 2 hours | Gabriel Badeo | 03.08.2024 | 1 | ts105 | https://drive.google.com/file/d/1N2SGk7WynUqmAKL6d_DHsgwnuBhqQI3e/view?usp=drive_link | 2 | High | ft_ts101 | peek_through_cards | lets the user peek through the topmost card of the deck | training_session | [12 empty] | https://drive.google.com/file/d/1NNLg3C6aVwJAuhFyAFO813s2T1uylm15/view?usp=drive_link | done | [6 empty] | prog_logic | Progress Analysis Logic | Ongoing
ts104 | As a user, I want to be able to reshift the bottommost card to top | 2 hours | Gabriel Badeo | 03.08.2024 | 1 | ts201 | https://drive.google.com/file/d/1N1uxu_JBExR0NbSljUjOuZx5OW6lzV4q/view?usp=drive_link | 2 | High | ft_ts102 | reduce_peeked_cards | lets the user reduce the number of peeked cards | training_session | [12 empty] | https://drive.google.com/file/d/1NNLg3C6aVwJAuhFyAFO813s2T1uylm15/view?usp=drive_link | done | [6 empty] | prog_ui | Progress/History Presentation UI | Ongoing
ts105 | As a user, I want to be able to return to the initial order of the deck | 2 hours | Gabriel Badeo | 03.08.2024 | 1 | ts202 | https://drive.google.com/file/d/1N1MLabmToVHWhRFqXq8VtjwubyQORXen/view?usp=drive_link | 2 | High | ft_ts103 | shift_card | lets the user shif the topmost card to the bottom of the active deck | training_session | [12 empty] | https://drive.google.com/file/d/1NNLg3C6aVwJAuhFyAFO813s2T1uylm15/view?usp=drive_link | done
ts200 | As a user, I want to be able to navigate through multiple decks | 2 hours | Gabriel Badeo | 03.08.2024 | 1 | ts301 | https://drive.google.com/file/d/1N1BZHNv7On-sag4RM9CVeASQL6zbhWMj/view?usp=drive_link | 2 | High | ft_ts104 | reshift_card | lets the user reshift the bottommost card to the top of the active deck | training_session | [12 empty] | https://drive.google.com/file/d/1NNLg3C6aVwJAuhFyAFO813s2T1uylm15/view?usp=drive_link | done
ts300 | As a user, I want to be able to abandon my session (hence leave it unrecorded) | 2 hours | Gabriel Badeo | 03.08.2024 | 1 | ts401 | https://drive.google.com/file/d/1N0jNGZnCejUoXIw6rIXtXM1n8t4uAf8Z/view?usp=drive_link | 2 | High | ft_ts105 | reset_order | lets the user reset the orer of the deck (first card in the order is the topmost one) | trainingg_session | [12 empty] | https://drive.google.com/file/d/1NNLg3C6aVwJAuhFyAFO813s2T1uylm15/view?usp=drive_link | done
os100 | As a user, I should be able to recite (input) the order of how I memorized the deck/s while the real sequence of cards is displayed side by side | 4 hours | Gabriel Badeo | 03.08.2024 | 1 | os101 | https://drive.google.com/file/d/1N4g_F-ECHj368cPqnfW4hB3DABzD2W8t/view?usp=drive_link | 2 | High | ft_ts201 | nav_inc_decks | lets the user move through decks increasingly (first deck to the next) | training_session | [12 empty] | https://drive.google.com/file/d/1NNLg3C6aVwJAuhFyAFO813s2T1uylm15/view?usp=drive_link | done
os200 | As a user, I should be able to fill up a list of the sequence of the cards I memorized | 4 hours | Gabriel Badeo | 03.08.2024 | 1 | os201 | https://drive.google.com/file/d/1N4Y0mKHzU4CFd_0g87mdAjR0MjNwVwSt/view?usp=drive_link | 2 | High | ft_ts202 | nav_dec_decks | lets the user navigate back through decks | training_session | [12 empty] | https://drive.google.com/file/d/1NNLg3C6aVwJAuhFyAFO813s2T1uylm15/view?usp=drive_link | done
os201 | As a user, I should be able to type/input the name of the card and list it as an entry in the sequence | 2 hours | Gabriel Badeo | 03.08.2024 | 1 | os202 | https://drive.google.com/file/d/1N4FVco1NJeWY3zb-FPG_Q4WngkquVES6/view?usp=drive_link | 2 | High | ft_ts301 | abandon_sess | lets the user leave the session without progress record | training_session | [12 empty] | https://drive.google.com/file/d/1NNLg3C6aVwJAuhFyAFO813s2T1uylm15/view?usp=drive_link | done
os202 | As a user, I should be able to edit the list | 2 hours | Gabriel Badeo | 03.08.2024 | 1 | os301 | https://drive.google.com/file/d/1N4BlEilOF9nLQx7_QLUpZueGHYLpRUEA/view?usp=drive_link | 2 | High | ft_ts401 | finish_session | lets the user finish the memorization session | training_session | [12 empty] | https://drive.google.com/file/d/1NNLg3C6aVwJAuhFyAFO813s2T1uylm15/view?usp=drive_link | done
p401 | As a user, I should be able to view automatically the results of my session immediately after submitting the order of how I memorized the cards, or after the recitation | 2 hours | Gabriel Badeo | 03.08.2024 | 1 | ps401 | https://drive.google.com/file/d/1N3gWPFZ4RE1V-dOcV8G6qjnIrR1M8jL_/view?usp=drive_link | 2 | High | ft_os101 | recite_deck | lets the user simultaneously compare/guess the each card in the ordered deck/s | ordering_session | [12 empty] | https://drive.google.com/file/d/1NNLg3C6aVwJAuhFyAFO813s2T1uylm15/view?usp=drive_link | done
p402 | As a user I should be able to see a graphical representation of the analysis and evaluation of my sessions and overall progress | 2 hours | Gabriel Badeo | 03.08.2024 | 1 | ps402 | https://drive.google.com/file/d/1N3GYGOuwI3_9Vz_4qbMojuJwXPZMR7mC/view?usp=drive_link | 2 | High | ft_os201 | fill_list | lets the user fill a sequence list of the guessed order of the deck/s memorized in the training session | ordering_session | [12 empty] | https://drive.google.com/file/d/1NNLg3C6aVwJAuhFyAFO813s2T1uylm15/view?usp=drive_link | done
[10 empty] | ft_os202 | edit_list | lets the user edit the list | ordering_session | [12 empty] | https://drive.google.com/file/d/1NNLg3C6aVwJAuhFyAFO813s2T1uylm15/view?usp=drive_link | done
[10 empty] | ft_os301 | show_result | let the user view memorization result of memorization and ordering of the training session | ordering_session | [12 empty] | https://drive.google.com/file/d/1NNLg3C6aVwJAuhFyAFO813s2T1uylm15/view?usp=drive_link | done
[10 empty] | ft_ps401 | show_history | lets the user view the results/stat of each training session | progress | [12 empty] | https://drive.google.com/file/d/1NNLg3C6aVwJAuhFyAFO813s2T1uylm15/view?usp=drive_link | done
[10 empty] | ft_ps402 | show_progress | lets the user view the overall progress | progress | [12 empty] | https://drive.google.com/file/d/1NNLg3C6aVwJAuhFyAFO813s2T1uylm15/view?usp=drive_link | done
PART II. SOFTWARE PROJECT FILE & TEST DATASET REQUIREMENTS
(A) Submit a zipped copy of the database with pre-migrated datasets which may be needed for testing use cases.
(B) Submit a zipped copy of your final software project containing the source code and its deployment(.exe file or URL)
(C) Submit a list of login credentials of sample user/s of your software. Make sure that these login credentials can be used to execute all test cases in your project.
(D) Submit a worksheet containing the list and/or details of the pre-migrated test datasets as a test reference.
(E) Submit a worksheet of your Data Management and related protocols.
Submitted by: |  |  |  | Date of Submission:
Nathaniel Enrique Catalan Eulin |  |  |  | 2024-02-25

## SampleRTM
Requirements Traceability Matrix (Sample Template)
Author: | Juan Luna
PROJECT TITLE: Hobbies Inventory System
PROJECT DESCRIPTION: User inventory of materials used in hobby, current skill profile/status, backlogs
TARGET USER/S: <Name of target user/s>
SDLC Used: <Name of SDLC which you will use in this project. Justify your choice.>
Technology Stack:
| a) Front-end: |  | <Enumerate the front-end technology stack you will use for this project. Justify your choice.>
| b) Back-end: |  | <Enumerate the back-end technology stack you will use for this project. Justify your choice.>
Note: Put all your files in your main Google Drive folder. Use your Full Name as the folder name during submission of the requirements below. The requirements below should be grouped in subfolders containing the same type of requirement/diagram.
PART I. SOFTWARE PROJECT REQUIREMENTS
(A) REQUIREMENTS ELICITATION | [5 empty] | (B) REQUIREMENTS SPECIFICATION | [15 empty] | (C) DESIGN MODELS (put at least one type of diagram per workflow dimension here. You can construct many diagrams of the same type depending on the size of your project requirements.) | [8 empty] | (D) IMPLEMENTATION | [7 empty] | (F) DEMO (Provide a link to recorded demo videos simulating the user stories/cases in the package)
[22 empty] | (C.1) CASE DIMENSION |  |  | (C.2) PROCESS DIMENSION |  |  | (C.3) RESOURCE DIMENSION
USER STORY | [5 empty] | (B.1) USE CASE |  |  |  | (B.2) Feature/Functionality |  |  |  | (B.3) GUI Storyboard (put all storyboards in one folder) |  |  | (B.4) TEST SPECIFICATION (update the status whenever applicable) |  |  |  |  | (C.1.1) Use Case Diagram (example) |  |  | (C.2.1) Sequence Diagram (example) |  |  | (C.3.1) Class Diagram (example) |  |  | (D.1) Package Diagram (Resource Dimension) |  |  | (D.2) Feature/Functionality (same as (B.2)) |  |  | (D.3) Schema (Provide a link to the screenshot/file of the Schema used per package
Story ID | Description | Cost Estimate | User | Date Recorded | Version No. | ID | Link to Use Case | Cost Estimate | Priority | ID | Name | Description | Module/Package | ID | Link to Diagram | Status (Ongoing/Completed/Cancelled/NA) | ID | Link to Test Case | Type of Test (Unit/Module/System/User Acceptance) | Status (Pass/Failed/NA) | Feedback/ Remarks | ID | Link to Diagram | Status (Ongoing/Completed/Cancelled/NA) | ID | Link to Diagram | Status (Ongoing/Completed/Cancelled/NA) | ID | Link to Diagram | Status (Ongoing/Completed/Cancelled/NA) | ID | Link to Diagram | Status (Ongoing/Completed/Cancelled/NA) | ID | Name | Status (Ongoing/Complete/Tested/Accepted/Cancelled) | ID | Link to Screenshot/File | ID | Link to Video Demo
# | <Description> | <cost estimate to develop story> | <put the name of the user who gave this requirement> | <Put the date this story is recorded as part of your project requirement> | <put the version number of the story, if the story was changed by the user> |  |  | <Provide your estimate on the cost of development for this use case> |  | # |  |  | <(candidate) module/package where the feature shall reside in> |  |  | <Status of creating the diagram> | [7 empty] | <Status of creating the diagram> | # |  | <Status of creating the diagram> |  |  | <Status of creating the diagram> | # |  | <Status of creating the diagram> | # |  | <Status of feature> | # |  | #
MHP01 | Manage Hobby Profile | 4 hours | Luna, Jaime | 2022-03-30 | 1 | MHP01_AddNewHobbyProfile | <insert link to Use Case for "Add Hobby Profile" here> | 1 hour | 1 | Add_New_Hobby | Add_New_Hobby_Profile | Get and save profile of new hobby of user | My Hobbies | NewHobbyGUI | <insert link of drawio file with GUI wireframe of this functionality> | Ongoing | NewHobby_SunnyDay |  | Unit | <indicate here whether or not your functionality has passed this test case> |  | Ucd_AddNewHobby | <insert link of drawio use case diagram of your use case of adding new hobby profile here, it can cover both sunny and rainy day scenario, i.e. adding is successful/fail because there is no existing hobby profile in the database.> | <indicate the status of completing this use case diagram>
NewHobby_RainyDay
[6 empty] | MHP01_UpdateHobbyProfile |  | 2 hours | 2 | Update_Hobby Profile
[6 empty] | MHP01_DeleteHobbyProfile |  | 1 hour | 3 | Delete_Hobby_Profile
PART II. SOFTWARE PROJECT FILE & TEST DATASET REQUIREMENTS
(A) Submit a zipped copy of the database with pre-migrated datasets which may be needed for testing use cases.
(B) Submit a zipped copy of your final software project containing the source code and its deployment(.exe file or URL)
(C) Submit a list of login credentials of sample user/s of your software. Make sure that these login credentials can be used to execute all test cases in your project.
(D) Submit a worksheet containing the list and/or details of the pre-migrated test datasets as a test reference.
(E) Submit a worksheet of your Data Management and related protocols.
Submitted by: |  |  |  | Date of Submission:
<Name of Student> |  |  |  | <Date>